## India
Date | Country | City | Qty (Interviews) | Est. Days (varies per req) | Notes
ARRIVAL |  |  | 30 May — Eid holidays 27–30 May
30 May | — | Mumbai | — | — | Arrival day. Interviews begin 31st May.
CONFIRMED — MUMBAI, NEW DELHI & CHANDIGARH |  |  | ~1,750 interviews ¦ 14 interview days
31 May – 5 Jun | India | Mumbai | ~750 | 6 days | 1 team: 100–120/day ¦ 2 teams: 200–240/day
6 Jun | ✈ Travel | Mumbai → New Delhi | — | 1 day
7 – 12 Jun | India | New Delhi | ~750 | 6 days | 1 team: 100–120/day ¦ 2 teams: 200–240/day
12 Jun (night) | ✈ Travel | New Delhi → Chandigarh | — | Same night | Night travel after last Delhi interview day.
13 – 14 Jun | India | Chandigarh | ~250 | 2 days | 1 team: 100–120/day ¦ 2 teams: 200–240/day
TOTAL |  |  | ~1,750
OPTIONAL — KOCHI (IF MORE REQUIRED) |  |  | Additional ~250 beyond confirmed plan
15 Jun | ✈ Travel | Chandigarh → Kochi | — | 1 day
16 – 17 Jun | India | Kochi | ~250 | 2 days | Only if additional interviews are required beyond the confirmed plan.
2 interview teams will reduce overall number of days to half

## International
Day | Country | City | Qty (Interviews) | Est. Days (varies per req) | Notes
BANGLADESH & PAKISTAN |  |  | Continues from India Day 16 (14 Jun, Chandigarh). Shifts +2 days if Kochi is added.
Day 17 | ✈ Travel | Chandigarh → Dhaka | — | 1 day | Departing after last India interview day.
Day 18–21 | Bangladesh | Dhaka | ~500 | 4 days | Apex team travels (subject to visa approval); local associates as backup.
Day 22 | ✈ Travel | Dhaka → Islamabad | — | 1 day
Day 23–26 | Pakistan | Islamabad | ~500 | 4 days | Handled via local associates. Apex team cannot travel to Pakistan.
TOTAL |  |  | ~1,000
REMAINING 500 — OPTION A: AFRICA |  |  | Preferred if local partner is secured
Day 27+ | Africa | — | 500 | TBD | No Apex office. Coordinating to source a local recruitment partner. Dates TBD.
REMAINING 500 — OPTION B: SRI LANKA & NEPAL |  |  | Alternative if Africa is not available
Day 27 | ✈ Travel | Islamabad → Colombo | — | 1 day | Departing after last Pakistan interview day (Day 26).
Day 28–29 | Sri Lanka | Colombo | ~250 | 2 days | Apex team will travel and conduct interviews.
Day 30 | ✈ Travel | Colombo → Kathmandu | — | 1 day
Day 31–32 | Nepal | Kathmandu | ~250 | 2 days | Apex team will travel and conduct interviews.
Day 33 | ✈ Depart | Kathmandu → Saudi Arabia | — | 1 day | Return flight.
TOTAL |  |  | ~500
2 interview teams will reduce overall number of days to half